WORK PACKAGE INTEGRATION CONFERENCE AGENDA

AND CHECKLIST

USS  ________________________               HULL NO.  _________________

TYPE OF AVAILABILITY  ______________

Ships Specification Package (SSP1) Number:  _____________DATE:  _____________

WORK PACKAGE INTEGRATION CONFERENCE (WPIC)

AGENDA CHECKLIST

# USS: ______________________________   HULL NO: ___________     SSP1: ___________

TYPE OF AVAILABILITY: _____________                  DATE: ______________

## CONFERENCE AGENDA

A.	REVIEW HABITABILITY ISSUES

1.	DISCUSS HABITABILITY IMPACT

2.	DISCUSS OFF-SHIP MESSING/OFF-SHIP BERTHING REQUIREMENTS

3.	DISCUSS AVAILABILITY OF BERTHING BARGE

4.	DISCUSS HABITABILITY “WORK AROUNDS” IF NO BERTHING BARGE WILL BE PROVIDED

5.	FOR BOQ/BEQ, VERIFY QUANTITY OF SHIP’S FORCE PERSONNEL

#### B.	REVIEW CRITICAL PATH / CONTROLLING ITEMS

##### C.	IDENTIFY REQUIREMENTS THAT THE SHIP MUST MEET PRIOR TO AVAILABILITY START

1.	DISCUSS AMMUNITION OFF-LOAD

2.	DISCUSS FUEL OFF-LOAD/ON-LOAD

3.	DISCUSS DEWATERING (COMPENSATED FUEL SYSTEMS)

4.	DISCUSS REEFER / STORES OFF-LOAD

##### D.	DISCUSS  NEW WORK, DELETIONS OR MAJOR REWRITES

1.	OBTAIN 2-KILOS FOR NEW WORK

2.	DOCUMENT SPECIFICATION DELETIONS

3.	IDENTIFY MAJOR SPECIFICATION REWRITES

##### E.	REVIEW ALTERATION INSTALLATION TEAM (AIT) REQUIREMENTS

1.	REVIEW QUARTERLY AIT SCHEDULE

2.	IDENTIFY AIT INSTALLATIONS SCHEDULED DURING AVAILABILITY

3.	OBTAIN 2-KILOS FOR ANY OUTSTANDING AIT SERVICES AND SUPPORT REQUIREMENTS

##### F.	REVIEW AIT INTERFACE PROBLEMS

##### G.	REVIEW POTENTIAL IMA AND SHIP’S FORCE INTERFACE PROBLEMS

1.	PORT ENGINEER RESOLVE POTENTIAL CONFLICTS

##### H.	REVIEW EARLY START AVAILABILITY REQUIREMENTS

1.	TYCOM ISSUE AVAILABILITY MESSAGE (IF REQUIRED)

##### I.	IDENTIFY ANY WORK ITEMS IN JEOPARDY

1.	GFM NOT AVAILABLE

2.	CUSTOMER FUNDING NOT AVAILABLE

3.	DRAWINGS / REFERENCES NOT AVAILABLE

4.	SCOPE OF WORK NOT DEFINED

5.	INSUFFICIENT AVAILABILITY DURATION

##### J.	DEFINE WORK THAT MUST BE STARTED BY A CERTAIN DATE (OTHER THAN OPTION ITEMS)

1.	IDENTIFY WORK START DATES

##### K.	DEFINE WORK THAT MUST BE ACCOMPLISHED BY PRODUCTION COMPLETION DATE (PCD)

1.	REVIEW AND SIGN LOA/PCD MILESTONE SHEET

##### L.	REVIEW TESTING REQUIREMENTS

1.	COMBAT SYSTEMS TESTS

2.	HM&E TESTS

3.	SPECIAL TEST/CERTIFICATION REQUIREMENTS

##### M.	REVIEW OPTION ITEMS AND INVOKE NLT DATES

##### N.	REVIEW LIST OF PRORATED WORK ITEMS

##### O.	REVIEW AVAILABILITY DURATION REQUIREMENTS

1.	REVIEW CONTRACT AND CNO DATES

2.	DETERMINE IF THERE IS SUFFICIENT TIME TO ACCOMPLISH SHIPALTS, MAJOR REPAIRS AND LOA REQUIREMENTS

##### P.	REVIEW REMAINING ADVANCE PLANNING AND CONTRACTING MILESTONES

1.	PLANNING ACTIVITY PROVIDE COPY OF AVAILABILITY STATUS REPORT (ASR)

##### Q.	REVIEW STATUS OF ANY OUTSTANDING CUSTOMER FUNDING REQUIREMENTS

##### R.	REVIEW UNRESOLVED BID SPEC REVIEW (BSR) REQUIREMENTS

##### S.	ASSIGN ACTION ITEMS AND COMPLETION DATES

##### T.	PROVIDE ALL WPIC ATTENDEES A COPY OF THE CONFERENCE ATTENDANCE LIST

##### U.	TYPE DESK ISSUE WPIC COMPLETION MESSAGE

WORK PACKAGE INTEGRATION CONFERENCE (WPIC)

USS: __________________________________      AVAILABILITY: ________         SSP1: ___________          DATE:___________

A.	HABITABILITY ISSUES

| Item Number/SWLIN | System/Equipment | Habitability Impact Major Minor |  | Remarks |
| --- | --- | --- | --- | --- |

| Off-Ship Messing Req’d? Yes No |  | Off-Ship Berthing Req’d? Yes No |  | Barge Assigned? Yes No |  | Work Around If Barge Not Available |
| --- | --- | --- | --- | --- | --- | --- |

| Quantities Of Ship’s Force Personnel (For BOQ/BEQ) | CO/XO | Officers | CPOs (E7 - E9) | Enlisted (E5 - E6) | Enlisted (E1 - E4) |
| --- | --- | --- | --- | --- | --- |
| Male |  |  |  |  |  |
| Female |  |  |  |  |  |

B.	CRITICAL PATH/CONTROLLING ITEMS

| CRITICAL PATH |  |  | CONTROLLING ITEMS |  |  |
| --- | --- | --- | --- | --- | --- |
| Item Number | Title | Mandays | Item Number | Title | Mandays |

C.	REQUIREMENTS THAT SHIP MUST MEET PRIOR TO AVAILABILITY START

| Event | Applicable? Yes No |  | Remarks |
| --- | --- | --- | --- |
| Ammunition Off-Load |  |  |  |
| Fuel Off-Load/On-Load |  |  |  |
| Dewatering (Compensated Fuel Systems) |  |  |  |
| Reefer/Stores Off-Load |  |  |  |

D.	NEW WORK, DELETIONS OR MAJOR REWRITES

New Work

| JCN Number | Nature of Work/Title | Remarks |
| --- | --- | --- |

Deletions

| JCN Number | Work Item Number | Remarks |
| --- | --- | --- |

Major Rewrites

| Work Item Number | Remarks |
| --- | --- |

E.	AIT INSTALLATIONS SCHEDULED TO BE ACCOMPLISHED DURING AVAILABILITY

| AIT Sponsor | Work To Be Accomplished By | AIT Point of Contact/Phone Number | Support Services Req’d Yes No |  | Installation Dates |
| --- | --- | --- | --- | --- | --- |

F.	AIT INTERFACE PROBLEMS

| AIT Installation | Installation Accomplished By | Interface Problems |
| --- | --- | --- |

G.	POTENTIAL IMA AND SHIP’S FORCE INTERFACE PROBLEMS

| JSN/SWLIN | Nature Of Work | Remarks |
| --- | --- | --- |

H.	EARLY START AVAILABILITY REQUIREMENTS

| JSN | Work Item | Proposed Availability Dates | Remarks |
| --- | --- | --- | --- |

I.	WORK ITEMS IN JEOPARDY

| JSN | Item Number | Reason for Jeopardy Status Material Funding Drawings Insufficient Time |  |  |  | Remarks |
| --- | --- | --- | --- | --- | --- | --- |

J.	WORK THAT MUST BE STARTED BY A CERTAIN DATE (OTHER THAN OPTION ITEMS)

| Work Item | Title | Start Not Later Than |
| --- | --- | --- |

K.	WORK THAT MUST BE COMPLETED BY PRODUCTION COMPLETION DATE (PCD)  Review and sign Key Event Worksheet - Attachment (1)

| Work Item | Title | Location | Description of Work To Be Accomplished |
| --- | --- | --- | --- |

L.	TESTING AND CERTIFICATION REQUIREMENTS

| Work Item | Title | Type of Test/Certification Required | Activity Responsible for Testing/Certification | Complete NLT |
| --- | --- | --- | --- | --- |

M.	OPTION ITEMS AND INVOKE NOT LATER THAN DATES

|  | Work Item Number | Title | Invoke Date (NLT) A - Date Calendar Date |  |
| --- | --- | --- | --- | --- |
| Option (1) |  |  |  |  |
| Option (2) |  |  |  |  |
| Option (3) |  |  |  |  |
| Option (4) |  |  |  |  |
| Option (5) |  |  |  |  |
| Option (6) |  |  |  |  |
| Option (7) |  |  |  |  |
| Option (8) |  |  |  |  |
| Option (9) |  |  |  |  |
| Option (10) |  |  |  |  |
| Option (11) |  |  |  |  |
| Option (12) |  |  |  |  |
| Option (13) |  |  |  |  |
| Option (14) |  |  |  |  |

N.	LIST OF PRORATED WORK ITEMS

| Work Item | Title | CNSL % | NAVSEA % | SHIPALT To Prorate Against S/A Number Title |  |
| --- | --- | --- | --- | --- | --- |

O.	AVAILABILITY DURATION REQUIREMENTS

Review the length of the Availability to determine if there is sufficient time to accomplish all SHIPALTs, major repairs and to support Light Off Assessment

P.	REMAINING ADVANCE PLANNING AND CONTRACTING MILESTONES

Planning Activity provide AVAILABILITY STATUS REPORT (ASR)

Q.	STATUS OF OUTSTANDING CUSTOMER FUNDING REQUIREMENTS

| Amount of Funding Required | Customer Responsible for Funding | Funds Required NLT | Remarks |
| --- | --- | --- | --- |

R.	UNRESOLVED BID SPEC REVIEW (BSR) REQUIREMENTS

| Work Item | Unresolved BSR Requirement/Issue | Action Required NLT Responsible Activity |  |
| --- | --- | --- | --- |

S.	ASSIGNED ACTION ITEMS AND COMPLETION DATES

| Work Item | Responsible Activity | Action Required | Complete NLT |
| --- | --- | --- | --- |

T.	WPIC LIST OF ATTENDEES    (Provide all attendees a copy)   -   Attachment (2)

U.	TYPE DESK ISSUE WPIC COMPLETION MESSAGE (including outstanding issues/concerns and action items)

# WORK PACKAGE INTEGRATION CONFERENCE

KEY EVENT WORKSHEET

USS  ______________________________     HULL NO.  ____________      SSP1  __________

| KEY EVENT/MILESTONE | A + DATE | SCHEDULE DATE |
| --- | --- | --- |
| START AVAILABILITY |  |  |
| COMPLETE INITIAL GAS-FREEING |  |  |
| DOCKING | NLT 25% |  |
| UNDOCKING | Contractor Provide |  |
| COMPLETE BILGE PRESERVATION (Complete Before PCD) |  |  |
| CREW MOVE ABOARD |  |  |
| FUEL SHIP |  |  |
| PRODUCTION COMPLETION DATE (Machinery Space Turnover) |  |  |
| START (LOA) TRAINING |  |  |
| START LIGHT-OFF ASSESSMENT (LOA) |  |  |
| PROPULSION PLANT LIGHT-OFF |  |  |
| START DOCK TRIAL |  |  |
| START FAST CRUISE |  |  |
| START SEA TRIAL |  |  |
| AEGIS LIGHT-OFF |  |  |
| COMBAT SYSTEM LIGHT-OFF |  |  |
| COMPLETE PIER-SIDE COMBAT SYSTEM TESTING |  |  |
| COMPLETE AVAILABILITY (CONTRACTOR) |  |  |
| COMPLETE AVAILABILITY (CNO) |  |  |

PORT ENGINEER:  ____________________________________  DATE ________________

SHIP REPRESENTATIVE:  _____________________________  DATE ________________

PROJECT MANAGER:  _________________________________ DATE ________________

ADV PLNG MANAGER:  ________________________________ DATE ________________

Attachment (1)

WORK PACKAGE INTEGRATION CONFERENCE (WPIC)

USS:  ________________  		AVAIL TYPE:  _____   		SSP1:  _____________

WPIC LOCATION:  _______________________________			DATE:  ___________

LIST OF ATTENDEES

| NAME | ACTIVITY/CODE | TELEPHONE | E-MAIL ADDRESS |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |
| 5. |  |  |  |
| 6. |  |  |  |
| 7. |  |  |  |
| 8. |  |  |  |
| 9. |  |  |  |
| 10. |  |  |  |
| 11. |  |  |  |
| 12. |  |  |  |
| 13. |  |  |  |
| 14. |  |  |  |
| 15. |  |  |  |
| 16. |  |  |  |
| 17. |  |  |  |

Attachment (2)